## Backlog
ID | Priority | Domain | Task | Why / Impact | Definition of Done | Effort | Dependencies | Agent | Status | References (URLs)
1 | P0 | Release/Architecture | Lock platform baseline to Open edX Ulmo + Tutor v21 and document version matrix | Ulmo is the current supported Open edX release (Dec 22, 2025) and brings major platform changes; Tutor v21 is the compatible installer baseline. A pinned matrix prevents “mystery upgrades” and reduces breakage. | A VERSION_MATRIX.md lists: Open edX release, Tutor version, enabled plugins, and git tags/images; CI enforces matrix via a check. | M |  | DevOps | In Progress | Tutor 21 (Ulmo) is the baseline. Image builds working. But custom Dockerfile was dead code — only Tutor-generated Dockerfile matters. Node 18 needed for learner-record (webpack 4).
2 | P0 | Release/Architecture | Run an Ulmo upgrade gap analysis + automated upgrade rehearsal (staging) | Ulmo spans changes up to Jan 15, 2026; upgrades can break customizations. Rehearsals surface data migrations, removed toggles, and theming changes before production. | Repeatable upgrade playbook + staging run completed; issues filed with severity; rollback plan validated. | L | 1 | DevOps+QA | Todo | No Ulmo upgrade gap analysis done. Running Ulmo but haven't audited what changed.
3 | P0 | Frontend/Theming | Migrate to Design Tokens theming end-to-end (legacy + MFEs + mobile readiness) | Ulmo requires the new Design Tokens theming system; there’s no overlap with the old theming approach. If you don’t do this, upgrades and UI consistency will stall. | Design token source-of-truth repo/package; Tutor build pulls tokens; MFEs load tokens; visual regression suite passes; legacy theme removed. | XL | 1,2 | Frontend+DevOps | In Progress | Design tokens partially working. Mereka theme compiles. But branding per-tenant is NOT working — SOF/BB show Mereka pink (#1383).
4 | P0 | Frontend/Architecture | Standardize MFE runtime configuration (stop baking config into builds) | Open edX supports configuring MFEs at runtime (not rebuild-time), improving upgrades, multi-site setups, and safer ops. | All MFEs read config via runtime config mechanism; config changes deploy without rebuilding MFE images; documentation added. | M | 1 | Frontend+DevOps | In Progress | MFE config API serves 12+ keys per tenant. SiteConfiguration cleanup automated. BUT: SiteConfig overrides accumulate stale data. ConfigMap hash wiring (#1478) prevents seamless deploy.
5 | P0 | Extensibility | Eliminate core forks/patched edx-platform by moving custom logic to plugins using Events/Filters (Hooks Extension Framework) | Plugin-first customization massively reduces upgrade pain. Hooks framework is explicitly designed for maintainable extension without core modification. | Inventory of all patches; each is replaced by a plugin (openedx-events/openedx-filters) or removed; edx-platform fork count reduced to zero or strictly minimized. | XL | 1,2 | Backend | In Progress | Tutor plugin architecture used. Custom apps in modules. BUT: 7 inline middleware copies across 3 overlays. Module imports from ConfigMap unreliable.
6 | P0 | Security/Compliance | PII & privacy hardening: audit PII, annotate, and automate retirement/erasure workflows | Enterprise customers will ask for GDPR-style controls and PII clarity. OEP-30 defines how Open edX treats PII and expects explicit handling. | PII inventory (DB + logs + exports) documented; PII markup applied where applicable; retirement runbook + tests; data retention policy published. | L | 1 | Backend+Security | Todo | No PII audit done.
7 | P0 | Product/Core | Confirm Learning MFE is the default courseware + remove any legacy courseware dependencies | The platform’s direction is MFE-first; relying on legacy courseware blocks upgrades and creates duplicate UI paths. | Legacy courseware disabled; redirects validated; customizations ported to MFE/plugin framework; no broken links. | M | 1 | Frontend+QA | In Progress | Learning MFE deployed. BUT: learner dashboard shows 403 'bff.has_read_access' error on dev. Profile page blank. NOT actually working for real users.
8 | P0 | Ops/SRE | Implement environment parity + one-command reproducible local/dev/staging (Tutor) | Most Open edX teams lose weeks to “works on my machine.” Tutor is the supported path; make it reproducible so agents can move fast. | make dev/up starts full stack; seeded data; smoke tests; env vars standardized; docs for new dev in <30 minutes. | M | 1 | DevOps | In Progress | 3 envs on RKE2 with ArgoCD. BUT: ConfigMap changes need hard refresh. Pod egress broken (#1460). Staging permanently Degraded (Ralph). NOT one-command reproducible.
9 | P0 | Ops/SRE | Backups + disaster recovery: automated DB/media backups, restore drills, and RPO/RTO targets | You can’t claim enterprise readiness without restore drills. Backups without tested restores are theater. | Daily backups (DB + S3/media); quarterly restore drill runbook; RPO/RTO documented; monitoring on backup jobs. | M |  | DevOps | In Progress | mysql-backup runs daily. auth-verify + cert-verify passing. BUT: restore drill NEVER done. ORA2/media on emptyDir. course-reindex blocked by networking.
10 | P0 | Security | Supply-chain security baseline: SBOM, image signing, secret scanning, dependency alerting | Open-source LMS in 2026 must prove provenance. This reduces incident risk and speeds vendor security reviews. | SBOM generated per release; images signed; secret scanning enabled; Renovate/Dependabot + SCA gating merged. | M | 1 | DevOps+Security | In Progress | Kyverno non-root + image signing policies. BUT: cosign GHCR auth fails for verification. No SBOM.
11 | P1 | Product/Core | Deploy the new Administrative Console + Roles & Permissions service (Ulmo MVP) | Ulmo introduces a shared roles & permissions system with a new Administrative Console entry point for managing library teams; adopting early reduces admin fragmentation and positions you for future RBAC expansions. | Admin Console MFE reachable from Studio; library team management works; admin audit verified; docs for operators. | M | 1,2 | DevOps+Frontend | In Progress | Admin Console MFE serves HTTP 200 with root div. BUT: not verified with real user — may have same issues as learner dashboard.
12 | P1 | Product/Core | Migrate Legacy Content Libraries to the new Libraries experience + validate role mapping | Ulmo’s roles/permissions MVP is library-first and legacy libraries don’t support it. Migration unlocks reuse workflows and reduces future breakage. | All legacy libraries migrated; spot-check content reuse; role assignments validated in console; no authoring regressions. | L | 11 | Backend+QA | Todo | Content Libraries v2 not migrated. Legacy libraries only.
13 | P1 | Product/Core | Enable Activity Notifications + Notification Preferences (tray + email) and tune retention/deliverability | Ulmo adds platform notifications with user preferences and automatic expiry; done right, this is a retention lever and reduces support load. | Bell tray + preferences working; email summaries deliver; DKIM/SPF/DMARC configured; retention verified; spam controls tested. | M | 1 | DevOps+Backend | Todo | Notifications not enabled.
14 | P1 | Product/Core | Adopt Ulmo Course Catalog Revamp and align it with Discovery/SEO strategy | Ulmo includes a catalog revamp (“beautiful course pages”). If you keep an old catalog path, you’ll fight the platform. | Course catalog pages enabled and themed; structured data/SEO checked; legacy catalog links redirected; analytics tracked. | L | 3,1 | Frontend+MarketingOps | Todo | Catalog revamp not done.
15 | P1 | Integrations | Implement Reusable LTI Configurations (central store) and standardize LTI 1.3 flows | Ulmo adds reusable LTI configurations, reducing repeated setup and configuration errors while improving security posture. | Central LTI configuration store enabled; course teams can reuse tools; migration doc; security review (key rotation). | M | 1 | Backend | Todo | LTI not configured.
16 | P1 | Enterprise/Security | Enterprise auth: implement OIDC/SAML SSO + optional MFA + SCIM-like provisioning (if needed) | Enterprise buyers expect SSO and centralized identity. Doing this cleanly avoids custom login hacks in MFEs. | SSO working for LMS+MFEs; documented IdP setup; automated user provisioning path; fallback login protected. | L | 4 | Backend+DevOps | In Progress | OIDC SSO via Authentik works for primary tenant. Studio SSO fixed. BUT: Enterprise SSO feature-flagged off. Multi-tenant OAuth chain works but Studio moment.js crash (#1385).
17 | P1 | Analytics/Data | Deploy Aspects analytics (Tutor plugin) for learner/instructor dashboards + data governance | Aspects is the community analytics solution for Tutor deployments; gives you actionable dashboards without building an analytics stack from scratch. | Aspects installed; pipelines running; dashboards reviewed; retention & access policy set; alerts for pipeline failures. | M | 1,9 | Data+DevOps | In Progress | Aspects ClickHouse + Superset on dev/staging. Prod dormant. Tracking logs ephemeral. ERB needs verification.
18 | P2 | Analytics/Data | Add a product metrics layer (North Star KPIs) tied to Open edX events | Aspects tells you ‘what happened’; KPIs tell you ‘are we winning’. Use events/filters to instrument business metrics without forking core. | Defined KPIs (activation, completion, retention); instrumentation via events; dashboards + weekly review cadence. | M | 17,5 | Data+Backend | Todo | No product metrics layer.
19 | P1 | Apps | Deploy Course Discovery service (catalog API) if you need programs, catalog APIs, or external marketing sites | Discovery is commonly required for catalog/program data and is a dependency for several commerce flows. | Discovery plugin enabled; catalog indexed; APIs documented; sync jobs monitored; course marketing pages verified. | M | 1 | DevOps+Backend | In Progress | Discovery service deployed. Health endpoint responds. BUT: discovery-sync CronJob status unverified after recent changes.
20 | P1 | Apps | Deploy Credentials service + Learner Record MFE (badges/certificates) | Teak/Ulmo emphasize credentials/badging; Credentials plugin brings Learner Record MFE and modern credential flows. | Credentials plugin enabled; badge/cert issuance tested; learner record accessible; secure signing/verification set. | M | 1,3 | DevOps+Backend | In Progress | Credentials deployed. Learner Record MFE builds and serves on prod. BUT: dev learner-record 404 (image tag stale). Actual learner record functionality unverified.
21 | P0 | Commerce | Decide commerce strategy: avoid deprecated Open edX Ecommerce; implement WooCommerce integration or external commerce via Coordinator | The legacy Ecommerce service and Tutor ecommerce plugin are deprecated/archived. A supported 3rd-party integration (e.g., WooCommerce) is the pragmatic path for most deployments. | Commerce decision doc; implemented integration (WooCommerce or other); purchase→enroll flow tested; monitoring + reconciliation. | L | 19 | Backend+DevOps | In Progress | Oscar deprecated. Purchase Gateway spec exists. BUT: no actual commerce working.
22 | P1 | Search | Confirm Meilisearch is configured as the platform search backend (Tutor default) and tune indexing | Meilisearch became the default search engine for Tutor-based deployments (Sumac). Ensuring it’s tuned improves discovery and reduces DB load. | Meilisearch enabled; index rebuild job; relevance tuned; monitoring; failover behavior documented. | S | 1 | DevOps | In Progress | Meilisearch deployed and healthy. Forum uses it. BUT: Django SEARCH_ENGINE still says ElasticSearchEngine. course-reindex can't reach MongoDB. Search not actually verified from user perspective.
23 | P1 | Discussions | Ensure discussions backend is the modern Python-based solution + deploy Discussions MFE + enable anti-spam controls | Recent releases migrated away from Ruby forums; Ulmo adds tools to limit spam. Aligning reduces maintenance and improves UX. | Discussions backend verified; discussions MFE enabled; spam controls configured; moderation runbook written. | M | 1 | Backend+DevOps | In Progress | Python openedx-forum in LMS. Discussions MFE serves. ENABLE_DISCUSSIONS_MFE set. BUT: not verified that forum content actually displays.
24 | P1 | Observability | Full-stack observability: logs, metrics, tracing, and error reporting (with SLOs) | You can’t improve reliability without visibility. SLOs convert ‘feels slow’ into measurable work for agents. | Dashboards for uptime, latency, errors; alerts tied to SLOs; tracing across LMS+MFEs; incident templates. | L | 8 | DevOps | In Progress | Prometheus + Grafana + Tempo + Loki on dev. ServiceMonitors deployed. BUT: alerting not proven end-to-end. No PagerDuty/Slack integration verified.
25 | P1 | Performance | MFE CDN + caching strategy (static assets, immutable builds, path routing if needed) | MFEs are heavy; CDN and good caching slash TTFB and bandwidth. Tutor ecosystem has plugins for MFE CDN/path routing patterns. | MFEs served via CDN; cache headers validated; smoke tests for routing; documented invalidation strategy. | M | 4 | DevOps+Frontend | Todo | No CDN configured. No caching strategy beyond Caddy defaults.
26 | P1 | Enterprise/Security | Harden auth/session security: secure cookies, HSTS, CSP, rate limiting, and bot protection | Open edX runs public endpoints; bot/spam and session theft are common threats. A baseline hardening checklist prevents low-effort attacks. | TLS+HSTS configured; CSP baseline; rate limiting; WAF rules; session cookie settings reviewed; security tests pass. | M |  | Security+DevOps | In Progress | Secure cookies with per-tenant domain scoping. JWT auth. Session middleware. BUT: SiteConfiguration stale overrides can break cookie domains.
27 | P2 | Multi-tenancy | If you run multiple brands: implement multi-site configuration + per-site theming via tokens + runtime MFE config | Multi-tenant deployments fail when branding is hardcoded. Tokens + runtime config makes multi-site viable without duplicating builds. | New site can be spun up with config-only changes; per-site tokens and MFE configs applied; regression tests for both sites. | L | 3,4 | Frontend+DevOps | In Progress | 3 tenants operational. Tenant-aware LMS redirect works. Studio OAuth tenant-aware. BUT: tenant homepages NOT branded per-tenant (#1383). Profile page broken. Learner dashboard BFF 403.
28 | P1 | Frontend/Architecture | Prepare for OEP-65 ‘Module Architecture’ adoption: track frontend-base/shell changes and minimize deep MFE forks | OEP-65 moves MFEs toward module federation with shared dependencies and new build/deploy concepts (frontend-base, projects). If you heavily fork MFEs now, you’ll pay twice later. | Tech radar doc; spike branch with module architecture; reduce custom MFE patches; plugin-slot approach where possible. | M | 4,5 | Frontend | Todo | No OEP-65 module architecture adoption.
29 | P2 | Accessibility/UX | Accessibility audit (WCAG) + fix theme token contrasts, keyboard navigation, and ARIA regressions in MFEs | Brand changes often break accessibility. Fixing early is cheaper than a compliance scramble for enterprise deals. | Audit report; prioritized fixes; automated a11y checks in CI; before/after screenshots and regression tests. | M | 3 | Frontend+QA | Todo | No WCAG audit done.
30 | P2 | Mobile | Mobile readiness: verify APIs, theming tokens, and feature parity for Open edX mobile apps | Design Tokens explicitly targets easier theming “including mobile applications.” If mobile is in your roadmap, bake readiness now. | Mobile integration checklist; token theming validated; critical learner flows tested in mobile; crash monitoring enabled. | M | 3 | Frontend+QA | Todo | Mobile readiness not verified.
31 | P1 | i18n | Adopt OEP-58 translation workflow (openedx-translations + openedx-atlas) across your custom repos/plugins | OEP-58 centralizes translations and expects repos to pull via atlas. If you keep ad-hoc translations, builds and upgrades will break. | atlas.yml present where needed; CI runs atlas pull/validate; translation updates no longer committed manually in your repos. | M |  | DevX | Todo | Translation workflow not adopted.
32 | P1 | Repo Hygiene | Refactor ‘customizations’ into a single Tutor plugin (e.g., tutor-mereka) with clear plugin slots and versioning | A plugin repository becomes the home for your delta (templates, settings, patches). This keeps your deployment upgradeable and reduces scattered hacks. | One Tutor plugin repo contains all overrides; semantic versioning; changelog; automated release builds; minimal config drift. | M | 5 | DevOps+Backend | In Progress | Tutor plugin + patches. BUT: 7 inline middleware copies across overlays. Dead Dockerfile confusion. apply-patches.sh is monkey-patching.
33 | P2 | Code Quality | Adopt unified lint/format/test tooling across Python and JS (ruff/black/mypy + eslint/prettier) with pre-commit | Agents move faster with guardrails. Consistent tooling reduces review load and prevents style debates. | pre-commit config; CI gates; autofix scripts; documented local setup; PR template includes checkboxes. | M |  | DevX | In Progress | ruff + shellcheck + eslint configured. 162 CI scripts. BUT: CI release-gate flakes. Footer parity script was checking wrong section names until today.
34 | P1 | Testing | Add end-to-end smoke tests for critical learner/author/admin flows (headless browser) in CI | Open edX upgrades often break in UI seams. Smoke tests are your ‘upgrade velocity insurance.’ | Smoke tests run on PR + nightly; cover login, enroll, learn, discussion, grading, author publish; flaky test budget defined. | L | 8 | QA+DevOps | In Progress | 162 static scripts. Fixture replay. Smoke accounts. BUT: NO real Playwright E2E. All 'proof' was curl HTTP 200 which misses JS errors, 403s, blank pages.
35 | P2 | API/Docs | Document and version all public integration APIs (OpenAPI where possible) and event contracts | Enterprise integrations fail on undocumented behavior. Explicit contracts reduce support and agent churn. | OpenAPI specs for your custom services; event payload contracts documented; breaking-change policy enforced. | M | 5 | Backend+Docs | Todo | No API documentation.
36 | P1 | Docs/Runbooks | Operational runbooks: upgrades, incidents, data fixes, email deliverability, and user support escalation | Scaling the team means institutionalizing knowledge. Runbooks turn tribal knowledge into repeatable execution for agents. | docs/runbooks/* created; on-call checklist; upgrade runbook includes Ulmo/Verawood steps; quarterly fire drill. | M | 2,24 | DevOps+Docs | In Progress | Troubleshooting runbook exists. CI/CD docs exist. BUT: restore drill runbook not created. Operational procedures incomplete.
37 | P2 | Branding | Brand system per OEP-48: single source for logos, colors, typography, footer/header links across legacy + MFEs | OEP-48 was created because MFEs fragment branding. Without a system, every new MFE becomes a theming one-off. | Brand assets repo; automated build packaging; applied to LMS+MFEs; documented brand guidelines for designers and devs. | M | 3 | Frontend+Design | In Progress | Brand package (@edx/brand) in MFE builds. Footer data in API. BUT: per-tenant branding NOT working. SOF/BB show Mereka colors.
38 | P2 | Repo Organization | Restructure repo into clear layers: platform config, custom plugins, themes/tokens, infra, docs | Most ‘deployment repos’ become junk drawers. Clear layering makes it obvious where changes go and prevents accidental coupling. | New directory structure; OWNERs; CODEOWNERS per area; migration guide; broken paths fixed. | M |  | DevX | Todo | Repo not restructured. Still flat scripts/ with 162+ files.
39 | P2 | DevX | Create a “golden path” dev environment (devcontainer or standardized docker compose + seed scripts) | Agents and new devs should get productive fast. Golden path prevents snowflake laptops and speeds onboarding. | Devcontainer/compose; seed demo org/course; scripts; docs; CI validates env build weekly. | M | 8 | DevOps+DevX | Todo | No golden path dev environment.
40 | P2 | Release Engineering | Release process: semantic versioning for your plugin/theme packages + changelog automation | Without disciplined releases, you can’t debug production or roll back safely. Agents need predictable release mechanics. | Tagged releases; automated changelog; release notes template; rollback tested; artifacts stored. | S | 32 | DevOps | Todo | No semantic versioning. No release process.
41 | P1 | Infrastructure | Infrastructure as Code: codify environments (K8s/Helm/Terraform) and remove manual console drift | Manual infra changes are invisible debt. IaC is the baseline for auditability and disaster recovery. | IaC repo/module; environment diffs detectable; secrets handled separately; drift detection pipeline. | L | 9 | DevOps | In Progress | RKE2 + ArgoCD + Kustomize. bbi-infrastructure repo. BUT: ConfigMap wiring broken (#1478). Vendor sync manual (#1387). Pod egress broken (#1460).
42 | P1 | Security | Secrets management overhaul: move from .env/values to Vault/Secrets Manager + rotation procedures | Keys leak. Rotation is often impossible if secrets are scattered. Centralize and automate. | All secrets in managed store; rotation runbook; CI prevents plaintext secrets; quarterly rotation drill. | M | 41 | Security+DevOps | Done | Infisical → ESO → K8s Secrets pipeline works. Machine identity auth. Pre-commit secret scanning.
43 | P2 | Governance | Adopt the Open edX deprecation/removal discipline internally (track DEPR items and remove dead code) | Open edX uses a formal deprecation process. Mirroring this keeps your fork/plugin surface small and upgradeable. | DEPR.md process; quarterly cleanup sprint; deprecated flags removed; migration notes for users. | S |  | Tech Lead | Todo | No deprecation discipline adopted.
44 | P2 | Data Governance | Data retention + export policy: define what you store, for how long, and how learners can export/delete | Privacy law and enterprise procurement require explicit policy. It also reduces storage cost and breach impact. | Policy doc; automated retention jobs; export endpoints/runbooks; user-request flow tested. | M | 6 | Backend+LegalOps | Todo | No data retention policy.
45 | P2 | Frontend/Customization | Move UI customization to supported plugin slots instead of patching MFEs | Ulmo/Teak add new frontend plugin slots, and OEP-65 continues the push toward composable frontends. Plugin slots reduce patch churn. | Inventory of MFE patches; replaced by plugin-slot implementations; upstream-friendly abstractions; documented. | M | 28 | Frontend | In Progress | Plugin slots partially used. Footer component. BUT: MFE slot ownership stripped by patch. Not fully migrated to plugin slots.
46 | P1 | CI/CD | Continuous Delivery pipeline for Tutor images/config: build, scan, sign, deploy to staging, run smoke tests | Release velocity + safety. If you can’t deploy to staging automatically, production will always be scary. | Pipeline exists; staging auto-deploy on main; smoke tests gate promotion; manual approval to prod; artifacts retained. | L | 10,34 | DevOps | In Progress | ARC runners build images. GHCR push works. Release object + truth ledger emit. BUT: dispatch blocked by GitHub App permissions. Manual promotion only.
47 | P2 | Supportability | Operational UX: admin tooling consolidation, support dashboards, and self-serve diagnostics for course teams | Most operator toil is repetitive triage. Giving course teams visibility reduces support tickets and speeds iteration. | Admin dashboard for common tasks; “diagnostics” page; documented escalation; reduced ticket volume baseline. | M | 11,24 | Backend+Frontend | Todo | No admin tooling consolidation.
48 | P2 | Cost/Scaling | Capacity planning + cost model (per active learner) with autoscaling and right-sizing levers | Scaling programs and enterprise contracts requires predictable unit economics. Cost-per-active-learner is the metric that forces discipline. | Cost dashboard; scaling policy; load tests; autoscaling configured; quarterly cost optimization backlog. | M | 24 | DevOps+FinanceOps | Todo | No capacity planning.
49 | P2 | Security/Enterprise | Audit logging: record key admin/user actions and expose export for compliance investigations | Enterprise audits ask: ‘who changed what, when?’ Audit logs reduce incident time-to-truth. | Audit log schema; logs shipped to SIEM; retention policy; export tooling; test cases for key actions. | M | 24,6 | Backend+Security | Todo | No audit logging.
50 | P3 | Roadmap | Set an ‘upgrade-every-release’ discipline: Verawood (Jun 2026) and Willow (Dec 2026) readiness plan | Open edX only supports the latest release. A standing upgrade cadence is the single highest leverage ‘debt reducer’ you can institutionalize. | Roadmap doc; quarterly upgrade rehearsals; release note triage process; budgeted upgrade sprint each cycle. | S | 2 | Tech Lead | Todo | No upgrade-every-release discipline.